## Read me
OWL VISION — TASK LIBRARY
Draft v0.3 — the checklist, not the estimates.
CHANGED IN v0.3
A-07 — audio owns comms outright, A2 leads. Video and cameras draw from it.
E-02 split — ground support (SL) and flown header (RIG, E-09) are now two rows.
A dependency written A / B means either one, never both. The only case is E-03.
WHAT CHANGED FROM v0.1
Durations and crew sizes are gone. They are a PM judgement on the job, not a
property of the task. A small wall is barely quicker than a big one, so a formula
would have been wrong in both directions.
This file answers WHAT HAS TO HAPPEN. The PM answers how long and how many.
HOW TO REVIEW IT
1. | Read the Task Library tab, department by department.
2. | Delete anything we never do. Add anything missing — that is the real work here.
3. | Check the Lead column. Blank means any hand can run it.
4. | Check Depends on. A wrong dependency puts a task in the wrong hour of the schedule.
THE COLUMNS
Task ID | Stable key. The scheduler references it, so do not renumber existing rows.
Task | One crew, one job. If it needs two different leads, it is two tasks.
Triggered by | The Production Scope tick in the PM app that makes this task appear.
Lead | Position that has to be present. Blank means any hand.
Phase | Load-in · Load-out · Both · Show day.
Depends on | Task IDs that must finish first.
Notes | Why it is here, or what goes wrong when it is skipped.
PHASE, AND WHY LOAD-OUT IS SHORTER
Load-in only covers commissioning — focus, tuning, colour match, content QC, dry run.
None of it has a load-out twin. Both means the task mirrors. Show day sits outside
the load-in schedule entirely. That is the whole reason strike is not load-in reversed.

## Task Library
Task ID | Task | Triggered by | Lead | Phase | Depends on | Notes
GENERAL — ALL HANDS |  | Always
G-01 | Truck dump, cases staged in the room | Always |  | Both |  | Everyone. Nothing else starts until this is done.
G-02 | Room walk with the venue contact | Always | PM | Load-in | G-01
G-03 | Mark stage, FOH and video village from the plot | Always | PM | Load-in | G-02 | Marking first saves moving a deck later.
G-04 | Dead cases to storage | Always |  | Both | G-01 | From the walkthrough answer. No answer means a hallway.
G-05 | Crew meal break | Always | PM | Both |  | Sits in the schedule so it does not get skipped.
G-06 | Safety walk — cable, ramps, edges, exits | Always | PM | Load-in |  | Before doors, every show.
G-07 | Client walkthrough and sign-off | Always | PM | Load-in | G-06
G-08 | Trash, sweep and venue handback | Always |  | Load-out
G-09 | Truck load and strap | Always |  | Load-out | G-08
POWER & GENERATOR |  | Power / Generator
P-01 | Confirm panel and drops with the house electrician | Power / Generator | PM | Load-in | G-02 | Walkthrough photo of the panel is the reference.
P-02 | Generator spot, grounding rod and fuelling | Power / Generator | PM | Load-in |  | Rod location must already be approved in writing.
P-03 | Distro build and feeder runs to each department | Power / Generator |  | Load-in | P-01
P-04 | Power up and load check per department | Power / Generator |  | Load-in | P-03
P-05 | Vendor tie-ins | Power / Generator | PM | Load-in | P-04 | Only if other vendors are drawing from us.
P-06 | Power down, distro and feeder strike | Power / Generator |  | Load-out |  | Last department out.
RIGGING & TRUSS |  | Rigging / Truss
R-01 | Confirm rig points against the plot | Rigging / Truss | RIG | Load-in | G-03
R-02 | Motors and chain set out | Rigging / Truss | RIG | Load-in | R-01
R-03 | Truss build on deck | Rigging / Truss | RIG | Load-in | R-02
R-04 | Department load onto truss | Rigging / Truss |  | Load-in | R-03 | Lighting and video hang their own. Rigger supervises.
R-05 | Trim check and lift to height | Rigging / Truss | RIG | Load-in | R-04
R-06 | Secondaries, safeties and sign-off | Rigging / Truss | RIG | Load-in | R-05
R-07 | Lower, strip truss, pack motors | Rigging / Truss | RIG | Load-out |  | First real load-out task. Everything hangs off it.
STAGING & SET |  | Staging
S-01 | Deck layout and level | Staging | SL | Load-in | G-03
S-02 | Legs, skirting and stair units | Staging | SL | Load-in | S-01
S-03 | Guardrails on every open edge | Staging | SL | Load-in | S-02 | MANDATORY at 29 inches or higher. Not a preference.
S-04 | Podium, furniture and set dressing | Staging |  | Load-in | S-02
S-05 | Stage strike and pack | Staging |  | Load-out
AUDIO |  | Audio
A-01 | PA fly or stack | Audio | A1 | Load-in | R-06
A-02 | Sub placement | Audio | A1 | Load-in | A-01
A-03 | Amp and drive rack build, network up | Audio | A1 | Load-in | P-04
A-04 | FOH console build and patch | Audio | A1 | Load-in | A-03
A-05 | Monitor world or IEM build | Audio | A2 | Load-in | A-03
A-06 | Mics, DIs, stands and stage cable | Audio |  | Load-in | A-04
A-07 | Comms and intercom distribution | Audio | A2 | Load-in | A-03 | Audio owns it end to end. Video draws from it — see V-04.
A-08 | System tune and time align | Audio | A1 | Load-in | A-06 | No load-out twin.
A-09 | Line check and soundcheck | Audio | A1 | Show day | A-08
A-10 | VOG and playback channel check | Audio | A1 | Show day | A-09 | Produced VOG file must already exist.
A-11 | Audio strike and case out | Audio |  | Load-out
LIGHTING |  | Lighting
L-01 | Fixture prep and bench check | Lighting | LX | Load-in | G-01
L-02 | Floor package position and cable | Lighting |  | Load-in | L-01
L-03 | Truss fixture hang | Lighting | LX | Load-in | R-03 | Happens on deck, before the lift.
L-04 | Data and power patch | Lighting | LX | Load-in | L-03
L-05 | Console build and patch to plot | Lighting | LD | Load-in | L-04
L-06 | Focus | Lighting | LD | Load-in | R-06 | Needs the truss at trim. No load-out twin.
L-07 | Programming and cue build | Lighting | LD | Load-in | L-06 | No load-out twin.
L-08 | Followspot positions and comms | Lighting |  | Load-in | L-05
L-09 | Lighting strike and case out | Lighting |  | Load-out | R-07
VIDEO & PROJECTION |  | Video / Projection
V-01 | Projector position or fly | Video / Projection | V1 | Load-in | R-06
V-02 | Screen build | Video / Projection |  | Load-in | G-03
V-03 | Focus, align and blend | Video / Projection | V1 | Load-in | V-02 | No load-out twin.
V-04 | Video village build — switcher and playback | Video / Projection | V1 | Load-in | P-04 | Comms comes from audio. A-07 first.
V-05 | Presentation laptops and confidence monitors | Video / Projection |  | Load-in | V-04
V-06 | Content load and slide QC | Video / Projection | V2 | Load-in | V-05 | Runs long when decks arrive late. No load-out twin.
V-07 | Cue to cue with presenters | Video / Projection | V1 | Show day | V-06
V-08 | Video strike and case out | Video / Projection |  | Load-out
LED WALL |  | LED Wall
E-01 | Stage carts and unpack panels | LED Wall |  | Load-in | G-01
E-02 | Ground support build | LED Wall | SL | Load-in | E-01 | Ground stack only. A flown wall uses E-09 instead.
E-09 | Flown header build and lift to trim | LED Wall | RIG | Load-in | R-03 | Flown wall only. Rigging owns it, not staging.
E-03 | Panel hang or stack | LED Wall |  | Load-in | E-02 / E-09 | Whichever of the two is in scope — never both.
E-04 | Data and power cabling | LED Wall |  | Load-in | E-03
E-05 | Processor build and panel mapping | LED Wall | V1 | Load-in | E-04
E-06 | Power up, colour match, dead pixel check | LED Wall | V1 | Load-in | E-05 | No load-out twin.
E-07 | Trim, mask edges and skirt | LED Wall |  | Load-in | E-06
E-08 | Wall strike, panel count and pack | LED Wall |  | Load-out |  | Count panels out. A missing panel found in the shop is a bad week.
CAMERAS & IMAG |  | Cameras / IMAG
C-01 | Camera positions — risers, tripods, cable | Cameras / IMAG |  | Load-in | G-03
C-02 | Fibre or SDI runs to video village | Cameras / IMAG |  | Load-in | C-01
C-03 | Camera comms and tally | Cameras / IMAG |  | Load-in | C-02, A-07 | Packs come off the audio loop.
C-04 | Shading and white balance | Cameras / IMAG | V1 | Show day | C-03 | No load-out twin.
C-05 | Camera strike and pack | Cameras / IMAG |  | Load-out
STREAMING & RECORDING |  | Streaming / Recording
T-01 | Confirm house internet or bond cellular | Streaming / Recording | PM | Load-in | G-02 | Walkthrough answer says which. Guest wifi is not bandwidth.
T-02 | Encoder build and bandwidth test | Streaming / Recording | V1 | Load-in | T-01
T-03 | Platform keys, destinations and dry run | Streaming / Recording | V1 | Load-in | T-02 | No load-out twin.
T-04 | Record decks armed and media checked | Streaming / Recording |  | Show day | T-02
T-05 | Media offload and hand to client | Streaming / Recording | V1 | Load-out |  | Do not leave the building without this signed off.
DRAPE & DECOR |  | Drape / Decor
D-01 | Pipe and base set out | Drape / Decor |  | Load-in | G-03
D-02 | Drape hang and steam | Drape / Decor |  | Load-in | D-01
D-03 | Masking check from audience sightlines | Drape / Decor | PM | Load-in | D-02
D-04 | Drape strike and fold | Drape / Decor |  | Load-out |  | Fold properly or the shop pays for it later.
SPECIAL EFFECTS |  | Special Effects
X-01 | Fire marshal inspection and permit on site | Special Effects | PM | Load-in |  | Permit must be in the Dropbox folder before the day.
X-02 | Effect position, safe zone and rigging | Special Effects |  | Load-in | X-01
X-03 | Test fire with the venue present | Special Effects | PM | Load-in | X-02 | No load-out twin.
X-04 | Effect strike and consumables count | Special Effects |  | Load-out
82 tasks across 12 departments. No single show pulls more than a third of them.
The PM sets crew and minutes per task on the job. Nothing in this file estimates time.